## Sheet1
Dublin Bikes Project Plan
Project Name | Dublin Bikes
Project Deliverable | Web Application
Start Date | 2019-02-11
End Date | 2019-04-19
Overall Progress | 0%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 | Stephen | 2019-02-11 | 2019-02-24 | 13 | Complete
Requirements | All | 2019-02-11 | 2019-02-24 | 13 | In Progress
Dublin Bikes API | Stephen | 2019-02-13 | 2019-02-21 | 8 | Complete
OpenWeather API | Stephen | 2019-02-13 | 2019-02-21 | 8 | Complete
Design Mockup | Kerrie | 2019-02-16 | 2019-02-21 | 5 | In Progress
RDS | Stephen | 2019-02-17 | 2019-02-20 | 3 | Complete
Sprint 2 |  | 2019-02-25 | 2019-03-10 | 13 | Not Started
Sprint 3 |  | 2019-03-11 | 2019-03-24 | 13 | Not Started
Sprint 4 |  | 2019-03-25 | 2019-04-07 | 13 | Not started
Complete
Overdue
In Progress
Not Started
Formulas:
Start = [Start, row below]