## Sprint 1
Sprint 1 Backlog |  |  | Sprint 1 (2 Weeks)
Product Backlog Item ID | User Stories (Features) | Initial Estimate - Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1 | Bikes API | 16 | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 3 | 2 | 3 | 0 | 2 | 0 | 0
a) Write script to read in
b) Upload script to EC2
c) Send data to Database
2 | Weather API | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1
a) Write script to read in
b) Upload script to EC2
c) Send data to Database
3 | Design - Sketch | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a) Do paper mockup
4 | RDS - Database Hosting | 13 | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0
a) Set up & Connect to EC2
b) Build Tables
5 | Requirements | 24 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 3 | 6 | 3 | 3 | 3 | 0
a) Requirements Gathering
b) User Reqirements
c) Functional & Non-functional Requirments
d) Appendix
6 | Design - Digital Template | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 0 | 0
a) Colour Scheme
b) UI/UX
7 | Administration | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0
a) Standups + Meetings
| Estimate Time | 75 | 74 | 72 | 70 | 70 | 64 | 57 | 50 | 47 | 38 | 24 | 15 | 5 | 1 | 0
|  | 58 | 2 | 2 | 2 | 2 | 5 | 6 | 9 | 4 | 3 | 2 | 9 | 7 | 2 | 3
| Actual Result | 58 | 56 | 54 | 52 | 50 | 45 | 39 | 30 | 26 | 23 | 21 | 12 | 5 | 3 | 0
Note on C2: Initial numeric estimate (size) concluded during Sprint Review

## Sprint 2
Sprint 2 Backlog |  |  | Sprint 2 (2 Weeks)
Product Backlog Item ID | User Stories (Features) | Initial Estimate - Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1 | Flask App | 38 | 2 | 2 | 3 | 4 | 5 | 4 | 4 | 2 | 2 | 3 | 3 | 3 | 1 | 0
a) HTML
b) CSS
c) Application Structure
2 | Database - Flask | 27 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 4 | 2
a) Connect to Flask
b) Execute the RestFUL API's
c) Format Results
3 | Database | 7 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
a) Review Scripts - Error Handling & Reliability
5 | Requirements | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2
a) Continue documentation
b) Reiew - add on features
d) Appendix
6 | Design - Digital Template | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1
a) Review
7 | Administration | 8 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1
a) Standups + Meetings
| Estimate Time | 89 | 85 | 80 | 75 | 70 | 63 | 57 | 49 | 41 | 35 | 26 | 18 | 11 | 6 | 0
|  | 75 | 2 | 7 | 3 | 8 | 6 | 4 | 3 | 5 | 7 | 5 | 7 | 8 | 4 | 6
| Actual Result | 75 | 73 | 66 | 63 | 55 | 49 | 45 | 42 | 37 | 30 | 25 | 18 | 10 | 6 | 0
Note on C2: Initial numeric estimate (size) concluded during Sprint Review